## MoSCoW Priorities
LIBRARY MANAGEMENT SYSTEM
MoSCoW prioritization for the first web release |  |  |  |  | 2026-10-08
Requirement source: the ten items in the user-supplied assignment brief.
Assumed constraints: 8-week first release, small web team, limited budget, existing catalog/member/loan data.
| Must-Have | Should-Have | Could-Have | Won’t-Have | Total requirements
| 3 | 2 | 3 | 2 | 10
Filter columns to review a category. Category dropdowns update the summary counts.
ID | Requirement | MoSCoW category | Impact on users and stakeholders | Feasibility: time, budget and resources | Why this priority?
LMS-01 | Add a feature to search books by title and author. | Must-Have | Readers find relevant books quickly. Librarians handle fewer routine discovery queries. This enables the online search-to-reservation journey. | Time: low effort for two searchable fields. Budget: reuse the existing catalog database. Resources: standard web and database skills. | Essential to the chosen release objective of online book discovery. A catalog that users cannot search would undermine that objective. Deliver title/author search before optional discovery features.
LMS-02 | Implement an online book reservation system. | Must-Have | Readers request books remotely. Librarians see requests consistently and allocate available copies without conflicting reservations. | Time: moderate rules and concurrency testing. Budget: reuse the web platform and database. Resources: backend development and librarian input. | Remote reservation is an assumed Release 1 objective. Deliver availability checks, reservation confirmation and cancellation first. Advanced queue policies can follow. Reassess if remote reservation leaves the launch objective.
LMS-03 | Generate monthly reports on borrowed books for administrators. | Should-Have | Administrators see borrowing trends and popular books. Librarians and managers can support collection planning and monthly oversight. | Time: low to moderate aggregation and export work. Budget: existing loan data limits extra cost. Resources: database/reporting skills and agreed metrics. | Important for oversight, but daily borrowing can continue without automated monthly reports. A manual loan-data export is a temporary alternative. Prioritize after the core reader and librarian workflows.
LMS-04 | Enable email notifications for overdue books. | Should-Have | Borrowers receive timely reminders. Librarians spend less time following up, and other readers benefit when books return sooner. | Time: moderate scheduling and delivery testing. Budget: allow for email-provider usage. Resources: valid email addresses, scheduler and delivery setup. | High operational value, but staff can temporarily contact overdue borrowers manually. Deliver reminders after the loan and due-date data are reliable. Missing contact data or email setup may delay this feature.
LMS-05 | Add support for QR code scanning for borrowing and returning books. | Could-Have | Librarians can process loans and returns faster with less typing. Readers may spend less time waiting at the desk. | Time: moderate labeling and device testing. Budget: QR labels and suitable scanning devices. Resources: scanner integration and staff training. | Useful efficiency improvement, but manual book/member ID entry supports the same circulation workflow. Protect core functions first. Raise the priority if transaction volume makes manual entry impractical.
LMS-06 | Create a user-friendly dashboard for librarians. | Must-Have | Librarians need a clear view of reservations, current loans and overdue books to perform daily work and respond to readers. | Time: moderate interface design and testing. Budget: reuse existing web infrastructure. Resources: frontend development and librarian feedback. | A basic operational dashboard is required to run the chosen digital circulation workflow. Include clear actions and current records. Advanced charts and custom analytics are outside the initial dashboard scope.
LMS-07 | Allow users to review and rate books. | Could-Have | Readers share experiences and choose books with community feedback. Librarians gain informal insight into reader preferences. | Time: moderate submission and moderation work. Budget: ongoing moderation time. Resources: review eligibility rules and a staff moderation process. | Improves engagement rather than essential circulation. Catalog details and librarian recommendations can support discovery initially. Add ratings/reviews only when core delivery and moderation capacity permit.
LMS-08 | Integrate a chatbot for user assistance. | Won’t-Have | Readers could obtain quick answers to common questions. Librarians could receive fewer repetitive support requests. | Time: added integration, content and fallback testing. Budget: bot-service and maintenance costs. Resources: support-content ownership and ongoing testing. | Defer for this release. Even a rules-based bot needs maintained answers and reliable escalation. A help page and contact option cover initial assistance. Reconsider when recurring support demand and an owner are established.
LMS-09 | Develop a mobile app version of the system. | Won’t-Have | Readers could gain convenient app access and device-specific features. Staff may also benefit from mobile access away from the desk. | Time: substantial additional app development and QA. Budget: distribution and platform maintenance. Resources: mobile development and device testing capacity. | Defer a dedicated mobile app for this release. Responsive web access meets the initial mobile-access need within the assumed constraints. Reconsider an app after core web workflows are stable and app-specific needs are confirmed.
LMS-10 | Provide multi-language support. | Could-Have | Additional languages improve access for readers and librarians who prefer another language, and may reduce misunderstandings. | Time: translation and layout/content testing. Budget: translation and review costs. Resources: localization work and fluent language reviewers. | The assumed launch audience can use English, so full localization can follow core workflows. Prepare text for later translation. Raise this to Should-Have or Must-Have if target users cannot use English or policy requires other languages.
How to interpret the categories
| Must-Have |  | Essential to the agreed release objective. Omission prevents a viable release. | Protect these capabilities before optional scope. | The minimum usable release for the chosen objective.
| Should-Have |  | Important, but a temporary workaround keeps the release usable. | Deliver after Must-Haves when capacity permits. | Omission causes significant operational inconvenience.
| Could-Have |  | Useful improvement with lower impact if omitted. | Use remaining capacity. Defer first when delivery is at risk. | Optional scope helps preserve time and budget flexibility.
| Won’t-Have |  | Excluded from this release. This is a deferral, not permanent rejection. | Reassess in a later release when need and resources are established. | No delivery commitment in the current release.
| MoSCoW method source |  | https://www.agilebusiness.org/resource/what-is-moscow-prioritization/ |  | Counts describe requirements, not development effort.
Classification assumptions
| Release objective |  | Readers find and reserve books online. Librarians manage circulation through a web dashboard. | Time and resources | Illustrative 8-week release with a small web team. No separate mobile-app or chatbot delivery stream.
| Budget and existing data |  | Limited budget. Catalog, member and loan records are available. Core circulation and authentication are assumed baseline capabilities. | Mobile access | Responsive web access is the initial mobile option. A dedicated mobile app is assessed separately as LMS-09.
| Language assumption |  | The intended launch audience can use English. Required languages and any access barriers were not specified. | When to revisit | Raise LMS-10 if users cannot use English or policy requires additional languages. Reassess other priorities if release goals or available resources change.